## Army
STATUS | CATEGORY | SYSTEM / FEATURE | KEY FILE(S) | DESCRIPTION | GAPS / NOTES
Unit Core
FULL PASS | Unit Core | Unit Class & Stats | unit.gd | unitType, unitLevel (1+), unitOffensiveScore, unitDefensiveScore, unitRangedOffence, unitRangedDefence, unitMagicDefence, unitMaxShield/unitShield. unitMaxManpower = 100 × level; unitMaxWeapons = 100 × level.
FULL PASS | Unit Core | Unit Attribute Calculation | unit.gd getUnitAttributes(), calculateGrossValues() | effectMultiplier = (man% + weapons%) / 2; artillery uses weapons% only. meleePenalty = 0.5 for muskets, 1.0 for sabers. offScore = level × weaponOffence × meleePenalty × effectMultiplier.
FULL PASS | Unit Core | Weapon / Ore / Armor Integration | unit.gd calculateWeaponsOresArmor() | Pulls stats from Weapon, Ore, Armor nodes; copies embedded milMods to unit.militaryModifierList. Shield = ore.oreMaxShield × unitLevel.
FULL PASS | Unit Core | Damage Reception (takeLosses) | unit.gd takeLosses(type, amount) | Melee: blocked = amount × unitDefensiveScore; shield absorbs first; rest = manpower. Ranged: same with unitRangedDefence. Magic: blocked = amount × unitMagicDefence; bypasses shield.
FULL PASS | Unit Core | Manpower Refill | unit.gd refillManpower(RR) | Adds armyReinforceRate to currentManpower each turn, capped at max. Skipped if army reinforcementBlocked flag is set.
FULL PASS | Unit Core | Mil Mod Tick (tick_temp_mods) | unit.gd tick_temp_mods() | Decrements turnsRemaining for all non-permanent mods (turnsRemaining > −1). Removes expired mods. Returns true if any removed (caller re-runs surveySelf).
Weapons
FULL PASS | Weapons | Saber Class (4 types) | weapon.gd | Cutlass L1 (+3/+2), Cavalry Saber L2 (+5/+3), Light Saber L3 (+7/+4), Heavy Saber L4 (+9/+5). reloadTurns=0; chargeManpowerCost=10%/charge. SaberCharge on all. CavalryMorale on L2, HeavyCharge on L4. | CavalryMorale and HeavyCharge mod effects declared but unimplemented.
FULL PASS | Weapons | Musket Class (4 types) | weapon.gd | Flintlock L1 (ranged +4, reload 2), Brown Bess L2 (+6, reload 2), Percussion Cap L3 (+8, reload 1), Lever Repeater L4 (+10, no reload, burns 2 ammo/lvl). All have Bayonet (melee at 50% penalty). VolleyFire on Brown Bess. | VolleyFire declared but unimplemented.
FIRST PASS | Weapons | Artillery Class (4 types) | weapon.gd | Falconet L1 (ranged +12, reload 3), Field Gun L2 (+18), Howitzer L3 (+25, reload 2), Mortar L4 (+35, reload 2, Siege mod). No melee. CannonBlast+AreaDamage on L2+. | AreaDamage and Siege effects unimplemented. Weapon cost calc uses legacy names → 0 cost shown.
FIRST PASS | Weapons | Mythic Weapons (9 event-unlock only) | weapon.gd | Baseball Bat, Trident, Mythic Atlatl, Sharps Carbine, Blackbeard's Pistols, Colt Revolver, Rocket Artillery, Trebuchet, Wright Flyer. Status effects on hit wired via battle.gd _apply_combat_status_effects(). is_mythic() helper defined. can_melee() excludes Rocket Artillery and Wright Flyer. | PirateVolley, CylinderFire, TrebuchetLaunch, AerialBombing special effects are stubs. RocketBarrage tile-fire effect not implemented.
FIRST PASS | Weapons | Legacy Weapon Class (12 types) | weapon.gd | Atlatl, Club, Double Axe, Flail, Longsword, Mace, Machete, Macuahuitl, Pike, Shortsword, Tomahawk, Spear. DODK compat. AtlatlPierce + ClubBleed mods applied. | Cost calc in surveySelf uses legacy names only — new weapon armies show 0 cost.
FULL PASS | Weapons | Reload System | unit.gd, battle.gd | reloadCounter counts down to 0 (ready). start_reload() sets counter=reloadTurns. GunCrewEfficiency reduces reloadTurns by 1 at start_reload(). get_effective_ranged_offence() returns 0 if reloading. | Reload only ticks during ranged rounds. Melee rounds do not advance reload.
Armor
FIRST PASS | Armor | Uniform Class (10 types) | armor.gd | Continental (DrillFormation), Redcoat (LineFormation), Militia, Light Infantry (Skirmish), Heavy Infantry (ShockTroop), Cavalry (MountedCharge+CavalryMorale), Artillery Corps (GunCrewEfficiency — WORKS), Minuteman (MinutemanSpirit), Tombstone Cap (QuickDraw), Hardee Hat (HardeeDisc). M/R/S block percentages defined on all. | Formation mods (Drill/Line/Skirmish/ShockTroop/Minuteman) declared at 'army level' but no army-level check exists. QuickDraw (first-attack bonus) and HardeeDisc (adjacent-friend bonus) are FIRST DRAFT stubs.
FIRST PASS | Armor | Legacy Armor Class (12 types) | armor.gd | Canine, Cast, Chain, Archer, Plate, Padded, Scout, Scale, Shell, Point, Feline, Otter. DODK compat. Chain adds to rangedOffence (inverted disabled bug historically). Shell has embedded spell block mod.
Mil Mod Pipeline
FULL PASS | Mil Mod Pipeline | MilMod Class (184 types defined) | mil_mod.gd | MilMod node: milModType, milModResource, disabled, turnsRemaining (−1=permanent), isNegative. Flag bools: infantryMod, rangedMod, siegeMod, commanderMod, civilianMod, resourceMod, marineMod, entrenchMod, terrainMod, toolMod, stormMod, culturalMod. buildSelf(Type) sets all flags from 184-entry match block.
FULL PASS | Mil Mod Pipeline | Commander Mod Tiers | governor.gd, army.gd commanderCheck() | Level codes: 123=all tiers, 23=tiers 2+3, 3=tier 3 only. commanderCheck() picks govMilModsLvl1/2/3 by governorLevel. VP commanders: all three arrays each appended twice (all mods doubled).
FULL PASS | Mil Mod Pipeline | Archetype Mod Assignment | world.gd _apply_archetype_mods() | 25 archetypes × 4 mods each: 2 at T1(123), 1 at T2(23), 1 at T3(3). Called after governorLevel=1 in generateBarracksCommanders().
FULL PASS | Mil Mod Pipeline | Resource Disable System | army.gd surveySelf(), mil_mod.gd disableMilModType() | surveySelf() resets all mods enabled, then calls disableMilModType(resource) for each depleted resource. Any mod whose milModResource matches depleted type gets disabled=true.
FULL PASS | Mil Mod Pipeline | calculateMilMods() | unit.gd calculateMilMods() | Main stat modifier function. Early return if armyDemoralized (skips all mod bonuses). Full match block for terrain/storm/cultural/commander/weapon/armor mods. Post-match generic state guard check: culturalMod + culturalState != '' + currentState == culturalState → +2 atk +2 def/level.
Terrain Mods
FIRST PASS | Terrain Mods | T1/T2/T3 Commander Terrain Mods (36 mods) | mil_mod.gd, unit.gd calculateMilMods() | All 36 commander mods have cases in calculateMilMods(). surveySelf() sets unit.currentTerrain + currentStorm before calling calculateMilMods(). Working: Woodsman, Swamp Legs, Hill Runner, Street Tough, Farmhand, Guerrilla Tactics, Backcountry Rider, Frontier Marksman, Everglades Tracker, Bayou Warrior, Continental Line, Last Stand, Saber Drill, Marksman, Steady Line. | Pending subsystems: Marine (now FIRST PASS), Entrenched (no turn counter), Night Raider (no night cycle), Ghost March (no ZoC), The Long March (no MP hook).
Storm Mods
FIRST PASS | Storm Mods | Storm Counter Mods (12 mods) | mil_mod.gd, unit.gd calculateMilMods() | Fog-Born, Storm Rider, Thunder Proof, Blizzard March, Hurricane Eyes, Tornado Dancer, Nor'easter Veteran, Rain Reader, White Out Walker, Storm Chaser, Lightning Rod, Eye of the Storm. stormMod=true + stormType; calculateMilMods reads currentStorm for stat bonuses. | Movement/immunity effects (Storm Rider, Blizzard March, Tornado Dancer, Storm Chaser) need army-level check.
Cultural Mods
FIRST PASS | Cultural Mods | Cultural / State-Specific Mods (12 mods) | mil_mod.gd, unit.gd calculateMilMods() | Country Musician (TN), Virginia Gentry (VA), Minuteman's Pride (MA), Quaker Steel (PA), Georgia Peach (GA), Backcountry Rider (SC), Harbor Watch (NY), Chesapeake Sailor (MD), Frontier Marksman (KY), River Runner (OH), Everglades Tracker (FL), Bayou Warrior (LA). | Minuteman's Pride (first-3-rounds +5 ATK) and River Runner (+2 movement near water) IDEA-tier.
State Guard Mods
FULL PASS | State Guard Mods | 26 State / Provincial Guard Mods | mil_mod.gd, unit.gd calculateMilMods() | PA, VA, NY, MA, MD, NC, SC, GA, CT, NJ, DE, NH, RI, VT, ME, TN, AL, FL, WV, DC, CA-QB, CA-OT, CA-NS, CA-NB, CA-PEI, BA. +2 attack +2 defence per level when in matching state tile. Generic post-match handler in calculateMilMods(): culturalMod + culturalState == currentState. | tileContinent must match culturalState codes exactly. No gate preventing wrong-state assignment.
Protector Buffs
FIRST PASS | Protector Buffs | 25 Protector Buff Mods (17 USA + 8 Canadian) | mil_mod.gd, army.gd _apply_status_effects_to_stats() | USA (17): Mothman Presence (+20 Rng/+15 Rng Def), Jersey Devil's Fury (+25 Atk), Bigfoot's Solidarity (+30 Block), Thunderbird's Sovereignty (+25 Ranged), Headless Terror (+20 Atk, attackers Terrified 2t), Chessie's Blessing (+20 Block), Bell Witch's Harassment (+15 Atk, attackers Demoralized 2t), Old Ironsides' Hull (+30 Shield), Valley Forge's Will (+10 Atk +25 Block +20 Def), Snallygaster's Claim (+20 Atk), Paul Revere's Ride (+15 Rng +3 Mvmt), Liberty Bell's Resonance (+25 Block), Green Mountain Haunting (+20 Block), Presidential Decree (+20 Atk +20 Block +15 Rng +15 Def), Skunk Ape's Domain (+20 Atk), Eternal Vigilance (+25 Block), Lincoln's Mandate (+15 Atk). Canadian (8): Le Wendigo (+30 Atk), Loup-Garou (+25 Atk), Feux Follets (+25 Rng Def), Mishepeshu (+20 Block/Rng Def), La Corriveau (+20 Rng), Le Carcajou (+20 Atk), La Chasse-Galerie (+15 Atk/Rng +4 Mvmt), Le Gougou (+15 Atk, attackers Terrified 3t). Applied as army status effects with magic upkeep; drain TotalMagic/turn; self-remove at 0. | Wiring 'cast_protector_buff' outcomes to specific protector AGREE events still needed. No UI shows active protector buffs or remaining magic upkeep cost.
Negative Status
FULL PASS | Negative Status | 22 Negative Status Effects | mil_mod.gd, army.gd _apply_status_effects_to_stats(), _apply_status_flags() | Combat: Stunned (no melee atk), Suppressed (no ranged atk), Shaken (block ×0.5), Terrified (atk ×0.5 block ×0.7), Routed (atk=0, no attack, def ×0.5 — triggered by >40% loss). DoT: Burning (5×unitCount/turn), Diseased (3×/turn), Quarantined (1×/turn + no reinforce). Stat: Blinded (ranged ×0.5), Hexed (magic def=0), Demoralized (atk ×0.8, block ×0.8, all mil mods disabled), Waterlogged (atk ×0.8, storm), Frostbitten (atk ×0.7, storm). Movement: Exhausted (movement → min 1), Bogged Down (movement = 0). Supply: Pacified (no attacks), Supply Cut (no reinforce). Funny: Seduced (no attack, atk=0), Starstruck (all ×0.7), Hangover (all ×0.5), Love-Struck (atk ×0.3, no attack), Mutinous (atk ×0.6, 50% refuse orders). | No UI displays active status effects on army. All 22 are mechanically wired.
Status System
FULL PASS | Status System | Army Status Effect System | army.gd apply_status(), _tick_status_effects(), _apply_status_effects_to_stats(), _apply_status_flags() | armyStatusEffects: Array of {type, turnsLeft, magicCostPerTurn}. apply_status(type, duration, magic_cost): refresh/replace if already present. _tick_status_effects() on onTurnEnd: magic upkeep drain for protector buffs (remove at 0); DoT for Burning/Diseased/Quarantined; tick and remove expired. _apply_status_effects_to_stats() from surveySelf(): all 47 stat modifiers (22 debuffs + 25 protector buffs). _apply_status_flags(): sets attackBlocked, reinforcementBlocked, movement from statuses. | No UI widget shows active statuses on army panel.
FULL PASS | Status System | Corruption Disease Check | army.gd onTurnEnd() | If inTile.tileCorrution > 0: randf() < corruption/100.0 → Diseased for 2 turns. Park Ranger mod (civilianMod + toolMod) grants full immunity. | Spelling 'tileCorrution' matches in-game variable.
FULL PASS | Status System | Storm Status Debuffs | world.gd _apply_storm_debuffs(), _apply_storm_status_to_army() | Applied at each turn start after _tick_storms(). Thunderstorm/Hurricane → Waterlogged 2t. Blizzard/Nor'easter → Frostbitten 2t. Fog → Blinded 1t. Tornado → Bogged Down 1t + Shaken 1t. | Armies moving into storm tiles mid-turn miss debuff until next turn start.
Combat
FULL PASS | Combat | Battle Class | battle.gd | Instantiated by army.calculateBattle(). Snapshots both army states. Calculates projected damage for display. Player clicks Attack to apply.
FULL PASS | Combat | Melee Damage Calculation | battle.gd _calculate_melee_damage() | raw_attack = attacker.armyPunch + _army_naval_supremacy_bonus(). block_ratio = armyBlock / unitCount (capped 0–0.9). Shield absorbs first; remainder hits manpower. Defender counter-attacks simultaneously.
FULL PASS | Combat | Ranged Damage Calculation | battle.gd _calculate_ranged_damage() | effective_launch = sum get_effective_ranged_offence() (0 if reloading). ranged_block_ratio = armyDefence / unitCount. Defender can counter-fire if ready. Double Shot / Double Cannonade second volley applied against remaining shield.
FULL PASS | Combat | Combat Status Effects | battle.gd _apply_combat_status_effects() | Routed: >40% manpower lost in one battle → Routed 2t. Weapon-based hits: Baseball Bat→Shaken, Trident→Terrified 2t, Mythic Atlatl→Stunned, Sharps Carbine→Blinded, Blackbeard's Pistols→Terrified, Colt Revolver→Shaken, Rocket Artillery→Burning 2t+Suppressed, Trebuchet→Stunned (ranged only), Wright Flyer→Suppressed. Protector retaliations: Bell Witch→Demoralize attacker 2t, Headless Terror→Terrify attacker 2t, Le Gougou→Terrify attacker 3t. | Weapon statuses fire on every attack, not just crits.
FULL PASS | Combat | Saber Charge Cost | battle.gd _apply_charge_costs(), unit.gd apply_charge_cost() | Each saber unit pays 10% × currentManpower on every melee attack. Applied after resolve.
FIRST PASS | Combat | Double Shot / Double Cannonade | battle.gd _calculate_ranged_damage() | Double Shot (T2): second volley at 50% power for artillery. Double Cannonade (T3): 100% + 3 bonus per artillery unit. Second shot calculated against remaining shield after first. | Only applies to artillery weapon class.
FULL PASS | Combat | Shield System | unit.gd, battle.gd | unitMaxShield = unitLevel × ore.oreMaxShield. Shield absorbs before manpower. Magic damage bypasses shield. restore_shield() resets at new engagement.
FULL PASS | Combat | Morale Multiplier | army.gd surveySelf() | mm = 1.0 + (commander.morale / 100) × 0.25. Applied to armyPunch + armyDefence. Range: ×1.0 (morale 0) to ×1.25 (morale 100). | governor.loyalty is −20 to +10; morale var may not be correctly initialized — multiplier may always be 1.0. See Major Bugs.
FULL PASS | Combat | Army Death (Civ-style) | army.gd, country.gd _on_army_destroyed() | manpowerInArmy ≤ 0 → emit armyDestroyed signal. country._on_army_destroyed(): erases from countryArmyList, nulls tile.stationedArmy, queue_free().
STUB | Combat | _apply_army_buff() — Army Buff Outcome | world.gd _apply_army_buff() ~line 3351 | Function called from event button outcomes but body is a single `pass` statement. All army_buff outcome types in events are silently ignored. | CRITICAL — implement: iterate countryArmyList, call army.apply_status(buff_type, duration).
Marine & Naval
FIRST PASS | Marine & Naval | Marine Mechanic | mil_mod.gd (marineMod), world.gd meleePressed(), path_point_button.gd navalPathPoints | Army with Marine mod may melee-attack into adjacent navalPathPoints (occupied PPBs). _army_has_active_marine() checks units for enabled Marine mod. meleePressed() loops inTile.navalPathPoints and builds battles on occupied ones. path_point_button.buildSelf() populates navalPathPoints from navalPathPointsEXP. | PPBs must be pre-wired in editor navalPathPointsEXP. No separate naval-target UI.
FIRST PASS | Marine & Naval | Naval Supremacy | battle.gd _army_naval_supremacy_bonus() | +5 × unitLevel added to raw_attack in _calculate_melee_damage() for armies with Naval Supremacy mod.
Army Core
FULL PASS | Army Core | Army Survey (surveySelf) | army.gd surveySelf() | Rebuilds all stats from units + milMods; applies morale multiplier; calculates resource costs; disables mods for depleted resources; sets unit.currentState = inTile.tileContinent; sets unit.armyDemoralized from _has_status(); calls _apply_status_effects_to_stats() at tail.
FULL PASS | Army Core | Turn-End Reset (onTurnEnd) | army.gd onTurnEnd() | currentMovementPoints = maxMovementPoints + _commander_movement_bonus(). Resets attackBlocked/reinforcementBlocked. Ticks spy timers. tick_temp_mods() per unit. _tick_status_effects(). _apply_status_flags(). Refills manpower if not reinforcementBlocked. Runs corruption disease check.
FULL PASS | Army Core | Commander Movement Bonus | army.gd _commander_movement_bonus() | Sums +3 for President mod and +3 for Election Season mod from govMilModsLvl arrays. Applied before _apply_status_flags() (Exhausted→min 1, Bogged Down→0).
FULL PASS | Army Core | Spy Effects (Sabotage / Recon) | army.gd | sabotaged bool + sabotageTimer: blocks movement/action for N turns. reconDebuffed bool + reconDebuffTimer: reduces armyDefence. Both tick on onTurnEnd(). | Wiring from espionage events to set flags is partial.
FIRST DRAFT | Army Core | Entrenched Mechanic | mil_mod.gd (entrenchMod flag) | entrenchMod bool defined. Design: after 3 stationary turns, +5 def/level; lost on movement. | No stationary turn counter. Nothing reads entrenchMod.
IDEA | Army Core | Unit Promotion / Experience | army.gd (averageExperience var) | averageExperience and armyLevel vars declared. No experience gain logic anywhere.
IDEA | Army Core | Formation Bonuses (Army-Level) | (DrillFormation, LineFormation, VolleyFire, ShockTroop, Skirmish mods) | Multiple weapon/armor mods reference formation bonuses. No army-level formation check exists.

## Events
STATUS | CATEGORY | SYSTEM / FEATURE | KEY FILE(S) | DESCRIPTION | GAPS / NOTES
Pipeline
FULL PASS | Pipeline | Event CSV Pipeline | EventDatabase.gd, world.gd, event_scene.gd | events.csv (260 events) + event_buttons.csv → evaluate_date_triggers() → createNewEvent() → event_scene.build_from_csv(). Events: event_id, headline, body, image_tag, content_flag. Buttons: event_id, button_id, text, outcome_type, outcome_value, outcome_amount, button_type, chain_event_id.
FULL PASS | Pipeline | Event Cooldown System | world.gd _event_cooldowns dict | _event_cooldowns dict; _event_on_cooldown() / _start_cooldown() / _tick_event_cooldowns(). Prevents same event firing again within cooldown window.
FULL PASS | Pipeline | Mission Flag System | world.gd mission_<id>_<tile> flags | Persistent boolean flags on world: set_mission_flag / set_mission_flag_own outcomes. checkPendingMissions() evaluates conditions each turn.
FULL PASS | Pipeline | Button Content Filtering | event_scene.gd _build_buttons() | button_type (standard/explicit/kinky_lewd/sensual) checked against player Settings. Explicit buttons hidden if player has content disabled. | No global Settings.enableExplicit toggle found — explicit always visible. See Major Bugs.
FULL PASS | Pipeline | Outcome Execution Engine | world.gd executeOutcome() | Handles 40+ outcome types: resource_change, loyalty_change, building_enable/disable, army_buff (STUB), promote_commander, morale_boost, add_tech, cast_protector_buff, set_mission_flag, add_governor, chain_event, tile_moral_decay_change, faction_loyalty_change, and more. | _apply_army_buff() is a critical stub (see Major Bugs).
Protector Events
FULL PASS | Protector Events | USA Protector 3-Stage Chain (17 × 3 = 51 events) | events.csv, world.gd _check_protector_summons() | PROT_01–17: each has PROT_xx_SUMMON → PROT_xx_TAME → PROT_xx_AGREE. SUMMON fires via _check_protector_summons() with wild corruption risk 25%/turn. All 17 protectors: Mothman, Jersey Devil, Bigfoot, Thunderbird, Headless Horseman, Chessie, Bell Witch, Old Ironsides, Valley Forge Spirit, Snallygaster, Paul Revere, Liberty Bell, Green Mountain Boys, Mount Rushmore Spirits, Skunk Ape, Eternal Minuteman, Lincoln's Ghost. Staggered turn thresholds per protector.
FULL PASS | Protector Events | Canadian Protector 3-Stage Chain (8 × 3 = 24 events) | events.csv, world.gd | CA_PROT_01–08: SUMMON → TAME → AGREE per protector. Le Wendigo, Loup-Garou, Feux Follets, Mishepeshu, La Corriveau, Le Carcajou, La Chasse-Galerie, Le Gougou.
Commander Arc
FULL PASS | Commander Arc | Commander Arc Events (25 arcs × 2 = 50 events) | events.csv, world.gd, WarRoomPanel.gd | ARC_01_FIRST–ARC_25_FIRST: fire when objective 1 complete. ARC_01_DONE–ARC_25_DONE: fire when all 3 objectives done. Fired via arcObjectiveCompleted signal from WarRoomPanel.
FULL PASS | Commander Arc | Governor Loyalty Arc Events (25 events) | events.csv, world.gd | GOV_LOYAL_ARC_01–25: fire at governor loyalty thresholds. One per archetype.
Tile Crisis
FULL PASS | Tile Crisis | 9 Tile Crisis Event Chains | world.gd, events.csv | Harvest Crisis, Harbor Crisis, Forge Crisis, Corrupt Event, Border Tension, Garrison Event, Legitimacy Crisis, Turncoat Warning, Memorial Restoration. All 9 wired with conditions + cooldowns. Fire on qualifying tile state.
Ualani Events
FULL PASS | Ualani Events | 9 Ualani Tile Events | world.gd _check_ualani_*(), events.csv | UALANI_AMBUSH_01, UALANI_DIGNITARY_01, UALANI_MEMORIAL_01, UALANI_WOUNDED_01, UALANI_WINTER_01, UALANI_FORGE_01, UALANI_CULPER_01, UALANI_ALLIANCE_01, UALANI_FRONTIER_01. All have cooldowns + location/condition checks. See Ualani tab for full breakdown.
FULL PASS | Ualani Events | 12 DC Monthly Events (WH_SECRET_01–12) | world.gd, events.csv | Trigger: Ualani at DC (tile 188) + matching calendar month (1–12). One-shot per month. Sensual/intimate tone. Several have explicit BTN2. | No UI indicator that a monthly event has already fired for the current month.
FULL PASS | Ualani Events | Chalchiuhtotolin Secret Arc (5 events) | world.gd, events.csv | CHALCH_SUMMON (Ualani at Plymouth tile 66 on month 11) → CHALCH_Q1 (build 3 farms) → CHALCH_Q2 (provide 150 food) → CHALCH_Q3 (build 5 farms) → CHALCH_AGREE (reward: +220 food total). | Ultra-rare trigger — player must know to position Ualani at Plymouth on month 11.
Calendar
FULL PASS | Calendar | Date / Calendar Events (DE_001–005) | EventDatabase.gd, event_triggers.csv | DE_001 New Year (month 1), DE_002 Valentine's Day (month 2), DE_003 Independence Day (month 7), DE_004 Halloween (month 10), DE_005 Mothman Day (month 11). Annual; evaluate_date_triggers() handles cooldowns.
City Events
FULL PASS | City Events | City Liberated / Lost Events | events.csv | CL_001 (NYC), CL_006 (Gettysburg), CL_007 (Kennett Sq.), CL_009 (Brattleboro), CL_182 (Nassau). CX_001 (DC falls), CX_005 (Gettysburg falls). Non-repeatable tile capture/loss events.
State Events
FULL PASS | State Events | State Liberated + Secession Events | events.csv, world.gd checkStateSecessionConditions() | SL_001 (Pennsylvania), SL_004 (Vermont). STATE_REBEL_01 (state secedes), STATE_REINTEGRATED_01 (rejoins). rebel_ flags per state drive the secession cascade.
Fort Events
FULL PASS | Fort Events | Fort Disrepair Chain (FORT_001–005) | world.gd, events.csv | FORT_001 → FORT_003 (public resolution) OR FORT_004 → FORT_005 (private/explicit path). FORT_005 is explicit-flagged.
Endgame Events
FIRST PASS | Endgame Events | Republic Collapse Events (COLLAPSE_01–02) | events.csv, world.gd _execute_republic_collapse() | COLLAPSE_01: 'THE REPUBLIC HAS FALLEN' — all metros lost, surrender terms. COLLAPSE_02: 'WASHINGTON STANDS ALONE' — fired directly from _execute_republic_collapse(). Both have explicit content buttons. | No game-over screen wired. Game continues after collapse events fire.
Misc Events
FULL PASS | Misc Events | Commander Turn Events (CMD_MERIT / CMD_RECOGNITION / CMD_THANKS) | world.gd _commander_turns, events.csv | Fire at 5 / 20 / 50 turns_served per governor. promote_commander outcome wired. CMD_THANKS has explicit button.
FULL PASS | Misc Events | VP / Canadian / UK / Peace Events | events.csv | VP_DOUBT, VP_BATTLEFIELD (VP relationship). CAN_PEACE_01, CAN_CLEARWATER, CAN_ELECTION, CAN_PEACE (Canadian diplomacy). PEACE_ALLIED, PEACE_USA (peace treaties). UK faction interaction events.
FULL PASS | Misc Events | Memorial, Stump Speech, Harvest, Harbor, Garrison | events.csv | MEMORIAL / MEMORIAL_RESTORE: specific tile memorial events. STUMP_SPEECH: political rally events. HARVEST / HARBOR / FORGE / GARRISON / BORDER: tile crisis single-instance events.

## Ualani
STATUS | CATEGORY | SYSTEM / FEATURE | KEY FILE(S) | DESCRIPTION | GAPS / NOTES
Identity
FULL PASS | Identity | Ualani Carlisle — President of the Republic | governor.gd buildSelf() | governorType='Ualani Carlisle'; isLeader=true; isVicePresident=false (she IS president). Base mods: Visionary×123, Champion of the Sun×23, Healer×3, President×123. _find_ualani_tile() locates her by governorType == 'Ualani Carlisle'. | Named governor mods (Visionary, Champion of the Sun) have no cases in calculateMilMods. Only President mod actively effects gameplay (movement bonus).
FULL PASS | Identity | isLeader Flag | governor.gd, world.gd | isLeader=true on Ualani. Used by world.gd to check head-of-state death condition. _game_ended checks isLeader to identify if protagonist is dead.
Commander Mechanics
FULL PASS | Commander Mechanics | President Mod (+3 Movement) | mil_mod.gd, army.gd _commander_movement_bonus() | commanderMod; +3 movement/turn. _commander_movement_bonus() sums +3 for President mod from govMilModsLvl arrays. Applied in onTurnEnd(): currentMovementPoints = maxMovementPoints + bonus, then status flags clamp.
FULL PASS | Commander Mechanics | Election Season Mod (+3 Movement, Permanent) | mil_mod.gd, world.gd _grant_election_season_mods(), _check_election_season() | _check_election_season() → _grant_election_season_mods(): grants 'Election Season' commanderMod to Ualani and any governor with isVicePresident=true. Permanent once granted. _commander_movement_bonus() sums +3 for this mod.
FULL PASS | Commander Mechanics | VP: All Mods Doubled | army.gd addUnitCommander() | isVicePresident=true governors get govMilModsLvl1/2/3 each appended twice (all mods doubled). VP also gains Election Season mod. Loyalty doubled during election season. | No dedicated VP appointment UI — isVicePresident set via event outcomes.
Tile Events
FULL PASS | Tile Events | UALANI_AMBUSH_01 — Ambush | world.gd _check_ualani_ambush() | Trigger: Ualani in Wetlands tile adjacent to UK-controlled tile. Cooldown 15t. Standard btn: +weapons 40. BTN3: explicit.
FULL PASS | Tile Events | UALANI_DIGNITARY_01 — Dignitary Reception | world.gd _check_ualani_dignitary() | Trigger: Ualani in Metro/Suburbs tile with Courthouse building. Cooldown 15t. Standard: −20 moral decay. BTN3: explicit.
FULL PASS | Tile Events | UALANI_MEMORIAL_01 — Memorial Address | world.gd _check_ualani_memorial() | Trigger: Ualani in tile with specialFeatures. Cooldown 15t. Standard: +morale 50. BTN3: explicit.
FULL PASS | Tile Events | UALANI_WOUNDED_01 — Field Hospital | world.gd _check_ualani_wounded() | Trigger: Ualani army < 80% manpower. Cooldown 15t. Standard: +manpower 40. BTN2: explicit.
FULL PASS | Tile Events | UALANI_WINTER_01 — Winter March | world.gd _check_ualani_winter() | Trigger: Ualani in Foothills/Woods tile, months 11–2. Cooldown 20t. No explicit button. Winter perseverance narrative.
FULL PASS | Tile Events | UALANI_FORGE_01 — Forge Inspection | world.gd _check_ualani_forge() | Trigger: Ualani in tile with enabled Forge building. Cooldown 15t. Standard: +weapons 60. BTN3: explicit.
FULL PASS | Tile Events | UALANI_CULPER_01 + UALANI_CULPER_BRIEF_01 — Culper Ring | world.gd _check_ualani_culper() | Trigger: Ualani in tile with espionage-active neighboring tile. Cooldown 15t. Standard: +gold 40 → chains to UALANI_CULPER_BRIEF_01; sets culper_active flag. BTN3: explicit.
FULL PASS | Tile Events | UALANI_ALLIANCE_01 — Alliance Council | world.gd _check_ualani_alliance() | Trigger: Ualani in tile with governor-occupied neighbor. Cooldown 15t. Standard: +loyalty 12. BTN3: explicit.
FULL PASS | Tile Events | UALANI_FRONTIER_01 — Frontier | world.gd _check_ualani_frontier() | Trigger: Ualani in Woods/Foothills tile bordering Canadian territory. Cooldown 15t. Standard: +morale 30. BTN3: explicit.
DC Monthly Events
FULL PASS | DC Monthly Events | WH_SECRET_01–12 (one per calendar month) | world.gd _check_white_house_monthly(), events.csv | Trigger: Ualani stationed at DC (tile 188) + current month matches (1–12). One-shot per month; cannot repeat until next year. Sensual/intimate narrative tone throughout. Several months have explicit BTN2. All 12 months fully authored. | No UI indicator that a monthly event has already fired for the current month.
Secret Arc
FULL PASS | Secret Arc | CHALCH_SUMMON — Chalchiuhtotolin Appears | world.gd, events.csv | Trigger: Ualani at Plymouth (tile 66) during month 11 (Thanksgiving). One-shot. Sets chalch_summoned flag. First contact with Aztec pestilence deity. | Ultra-rare — player must know to position Ualani at Plymouth in November.
FULL PASS | Secret Arc | CHALCH_Q1 / Q2 / Q3 — Three Tasks | world.gd, events.csv | Q1: Build 3 farms in republic territory. Q2: Provide 150 food as tribute. Q3: Build 5 farms total. Each task unlocks after prior is complete. Progressive resource rewards at each stage.
FULL PASS | Secret Arc | CHALCH_AGREE — Alliance Sealed | world.gd, events.csv | Final arc event after all 3 tasks complete. Total reward: +220 food. Chalchiuhtotolin pledges support to the Republic narrative.
Election System
FULL PASS | Election System | Election Season + VP Succession | world.gd _check_election_season(), _grant_election_season_mods() | _check_election_season() fires UALANI_ELECTION_01 event and calls _grant_election_season_mods(). VP governor gets isVicePresident=true, Election Season mod, doubled mods, doubled loyalty. _game_ended flag checked to prevent election loop during game over. | No VP appointment UI. VP status set by event outcomes.
Endgame
FIRST PASS | Endgame | Republic Collapse — Ualani's Last Stand | world.gd _execute_republic_collapse() | On collapse: UK receives coastal tiles. Interior tiles spawn state nations. USA retains only DC (tile 188) — Ualani's final stronghold. COLLAPSE_02 'Washington Stands Alone' fires from this function. Explicit content option. | Game continues after collapse. No rebuild-from-DC win path currently defined.
FIRST DRAFT | Endgame | Head of State Death → Game Over (STUB) | world.gd ~line 4001 | _game_ended bool flag exists and is checked in election logic. Priority comment in code: 'head of state death → game over (Ualani for USA)'. TODO comment: '# call _trigger_game_over() once game over screen exists'. | Game over screen not built. Death has no mechanical consequence yet. High priority for ship.

## Explicit Content
SYSTEM | STATUS | DESCRIPTION
EXPLICIT CONTENT SYSTEM OVERVIEW
Content Flag System | FULL PASS | events.csv content_flag column + event_buttons.csv button_type column. Values: standard, explicit, kinky_lewd, sensual. event_scene.gd _build_buttons() checks button_type before rendering.
Explicit Content Gating | STUB | button_type filtering exists in event_scene.gd but no global Settings.enableExplicit flag found. Explicit buttons always displayed — no parental control or age-gate. HIGH PRIORITY before public release.
Total Explicit Buttons | FULL PASS | ~29 explicit-flagged buttons + ~15 sensual buttons + ~2 kinky_lewd buttons = ~44 adult-content buttons. Spread across protector events, commander events, Ualani tile events, DC monthlies, fort chain, collapse events, VP events, Canadian events.
Explicit Events in events.csv | FULL PASS | CMD_THANKS (explicit), FORT_005 (explicit), PROT_01_SUMMON (kinky_lewd), CAN_PEACE_01 (explicit), WH_SECRET_07 (explicit). PROT_01_AGREE, PROT_14_AGREE, PROT_14_SUMMON also kinky_lewd flagged.
EXPLICIT / KINKY-LEWD / SENSUAL BUTTONS (from event_buttons.csv)
EVENT ID | HEADLINE | CONTENT FLAG | BTN TYPE | BUTTON TEXT | OUTCOME | BTN ID
CMD_THANKS | PRESIDENT CARLISLE DELIVERS PERSONAL THANKS TO [COMMANDER_NAME] AT [TILE_NAME] | explicit | explicit | The Full Presidential Visit | morale_boost | CMD_THANKS_BTN2
FORT_005 | CLASSIFIED DIPLOMATIC PROCEEDINGS AT [TILE_NAME] | standard | explicit | The Full Classified Briefing | morale_boost | FORT_005_BTN1
COLLAPSE_02 | WASHINGTON STANDS ALONE | standard | explicit | The Long Night | morale_boost | COLLAPSE_02_BTN1
HARVEST_VISIT_01 | PRESIDENT CARLISLE SAVES THE HARVEST | standard | explicit | Presidential Persuasion — Full Agricultural Engagement | resource_change → food | HARVEST_VISIT_01_BTN2
UALANI_AMBUSH_01 | CROWN AMBUSH AVERTED: PRESIDENT CARLISLE HOLDS THE WETLANDS | true | explicit | The Full Counteroffensive Briefing | resource_change → weapons | UALANI_AMBUSH_BTN3
UALANI_DIGNITARY_01 | STATE RECEPTION AT [TILE_NAME]: PRESIDENT CARLISLE ATTENDS IN FULL CAPACITY | true | explicit | The Full Presidential Reception | tile_moral_decay_change | UALANI_DIGNITARY_BTN3
UALANI_MEMORIAL_01 | PRESIDENT CARLISLE VISITS [TILE_NAME]: PRESIDENTIAL ADDRESS AT THE MEMORIAL | true | explicit | The Full Memorial Ceremony | morale_boost | UALANI_MEMORIAL_BTN3
UALANI_WOUNDED_01 | PRESIDENT CARLISLE VISITS FIELD HOSPITAL AT [TILE_NAME] | true | explicit | Full Field Hospital Authorization | resource_change → manpower | UALANI_WOUNDED_BTN2
UALANI_FORGE_01 | PRESIDENT CARLISLE CONDUCTS SURPRISE INSPECTION OF FORGE AT [TILE_NAME] | true | explicit | The Full Forge Inspection | resource_change → weapons | UALANI_FORGE_BTN3
UALANI_CULPER_01 | CULPER RING CONTACT AT [TILE_NAME]: INTELLIGENCE ASSET REQUESTS MEETING | true | explicit | The Full Culper Meeting | resource_change → gold | UALANI_CULPER_BTN3
UALANI_ALLIANCE_01 | PRESIDENT CARLISLE MEETS WITH [COMMANDER_NAME] AT [TILE_NAME] | true | explicit | The Full Alliance Council | governor_loyalty_change | UALANI_ALLIANCE_BTN3
UALANI_FRONTIER_01 | PRESIDENT CARLISLE ESTABLISHES FRONTIER PRESENCE AT [TILE_NAME] | true | explicit | The Full Frontier Address | morale_boost | UALANI_FRONTIER_BTN3
PROT_01_AGREE | MOTHMAN FORMALLY ALLIES WITH THE CONTINENTAL REPUBLIC | kinky_lewd | kinky_lewd | The Complete Accord at Harper's Ferry | set_flag → prot_01_agreed | PROT_01_A_BTN2
PROT_02_AGREE | JERSEY DEVIL FORMALLY ENDORSES THE CONTINENTAL CAUSE | standard | explicit | The Full Pine Barrens Meeting | set_flag → prot_02_agreed | PROT_02_A_BTN2
PROT_03_AGREE | BIGFOOT FORMALLY GUIDES THE CONTINENTAL CAUSE THROUGH THE MOUNTAINS | standard | explicit | The Full Mountain Agreement | set_flag → prot_03_agreed | PROT_03_A_BTN2
PROT_04_AGREE | THUNDERBIRD FORMALLY ALLIES WITH THE CONTINENTAL REPUBLIC | standard | explicit | The Full Ceremonial Alliance | set_flag → prot_04_agreed | PROT_04_A_BTN2
PROT_05_AGREE | THE HORSEMAN RIDES FOR THE REPUBLIC — FORMALLY | standard | explicit | The Full Hudson Valley Accord | set_flag → prot_05_agreed | PROT_05_A_BTN2
PROT_06_AGREE | CHESSIE FORMALLY PATROLS FOR THE CONTINENTAL NAVY | standard | explicit | The Full Chesapeake Accord | set_flag → prot_06_agreed | PROT_06_A_BTN2
PROT_07_AGREE | THE BELL WITCH FORMALLY COMMITS TO THE CONTINENTAL CAUSE | standard | explicit | The Full Tennessee Alliance | set_flag → prot_07_agreed | PROT_07_A_BTN2
PROT_08_AGREE | OLD IRONSIDES FORMALLY JOINS THE CONTINENTAL NAVY | standard | explicit | The Full Naval Recommissioning | set_flag → prot_08_agreed | PROT_08_A_BTN2
PROT_09_AGREE | VALLEY FORGE GUARDIAN FORMALLY BLESSES THE CONTINENTAL ARMY | standard | explicit | The Full Valley Forge Ceremony | set_flag → prot_09_agreed | PROT_09_A_BTN2
PROT_10_AGREE | SNALLYGASTER FORMALLY GUARDS THE CONTINENTAL SUPPLY NETWORK | standard | explicit | The Full Maryland Agreement | set_flag → prot_10_agreed | PROT_10_A_BTN2
PROT_11_AGREE | PAUL REVERE FORMALLY INTEGRATES WITH CONTINENTAL INTELLIGENCE | standard | explicit | The Full Intelligence Alliance | set_flag → prot_11_agreed | PROT_11_A_BTN2
PROT_12_AGREE | THE LIBERTY BELL FORMALLY RINGS FOR THE REPUBLIC | standard | explicit | The Full Independence Hall Accord | set_flag → prot_12_agreed | PROT_12_A_BTN2
PROT_13_AGREE | GREEN MOUNTAIN GHOST FORMALLY PROTECTS VERMONT FOR THE REPUBLIC | standard | explicit | The Full Green Mountain Ceremony | set_flag → prot_13_agreed | PROT_13_A_BTN2
PROT_14_AGREE | THE RUSHMORE COUNCIL FORMALLY ENDORSES PRESIDENT CARLISLE | kinky_lewd | kinky_lewd | The Complete Presidential Council | set_flag → prot_14_agreed | PROT_14_A_BTN2
PROT_15_AGREE | SKUNK APE FORMALLY PATROLS FLORIDA FOR THE CONTINENTAL REPUBLIC | standard | explicit | The Full Everglades Accord | set_flag → prot_15_agreed | PROT_15_A_BTN2
PROT_16_AGREE | THE MINUTEMAN FORMALLY DECLARES FOR THE CONTINENTAL REPUBLIC | standard | explicit | The Full Lexington Green Ceremony | set_flag → prot_16_agreed | PROT_16_A_BTN2
PROT_17_AGREE | LINCOLN FORMALLY ENDORSES PRESIDENT CARLISLE'S ADMINISTRATION | standard | explicit | The Full Presidential Consultation | set_flag → prot_17_agreed | PROT_17_A_BTN2
STUMP_SPEECH_01 | PRESIDENT CARLISLE TAKES THE FLOOR AT [TILE_NAME] — THE CAMPAIGN IS HERE | standard | explicit | The Full Presidential Address | election_pressure_change | STUMP_BTN2
VP_DOUBT | THE VICE PRESIDENT AT 2 A.M.: [COMMANDER_NAME] IS QUESTIONING EVERYTHING | false | sensual | Remind Them in a More Convincing Way | morale_boost | VP_DOUBT_BTN2
VP_BATTLEFIELD | THE VICE PRESIDENT PICKS UP A MUSKET: [COMMANDER_NAME] AT THE FRONT LINE | false | explicit | More Than Standing Beside Them | morale_boost | VP_BATTLEFIELD_BTN2
VP_PRE_ELECTION | THE VICE PRESIDENT CALLS AN UNSCHEDULED MEETING — [COMMANDER_NAME] ISN'T SURE THEY WANT TO RUN | false | explicit | Convince Them to Stay In the Race | morale_boost | VP_PRE_ELECTION_BTN2
VP_LEGACY | THE VICE PRESIDENT LEAVES A NOTE — [COMMANDER_NAME] HAS SOMETHING TO SAY | false | explicit | This Has Always Been Personal | morale_boost | VP_LEGACY_BTN2
CAN_CLEARWATER_01 | PM CLEAR-WATER'S PRIVATE CHANNEL: JESSICA WRITES OUTSIDE OFFICIAL CHANNELS | false | sensual | Answer the Way the Question Was Really Asked | set_flag → can_clearwater_close | CAN_CLEARWATER_BTN2
CAN_JOINT_OPS_01 | JOINT INTELLIGENCE SUMMIT: THREE GOVERNMENTS SHARE ONE MAP | false | explicit | The Full Joint Operation — All Three Committed | morale_boost | CAN_JOINT_OPS_BTN2
CAN_SUMMIT_01 | THE OTTAWA SUMMIT: ALL THREE IN THE SAME ROOM FOR THE FIRST TIME | standard | explicit | The Full Ottawa Summit — All Diplomatic Protocols Observed | set_flag → can_summit_complete | CAN_SUMMIT_BTN2
CAN_ALLIANCE_SIGNED | THE CONTINENTAL DEFENSE ALLIANCE IS SIGNED: THREE NATIONS — ONE FRONT | standard | explicit | The Full Ratification Ceremony — All Three in Agreement | form_alliance → CA | CAN_ALLIANCE_BTN2
CAN_PEACE_01 | THE TIDE HAS TURNED: PENOIT AND CLEAR-WATER COME TO WASHINGTON | standard | explicit | The Full Continental Peace Proceedings | morale_boost | CAN_PEACE_BTN2
CAN_ELECTION_LUCK | PM CLEAR-WATER'S CALL: JESSICA HAS SOMETHING TO SAY BEFORE THE ELECTION | false | sensual | Say the Thing That Cannot Be Said After the Results | election_pressure_change | CAN_ELECTION_BTN2
CA_PROT_01_AGREE | LE WENDIGO STANDS DOWN: SAINT-GEORGES FOREST ACCORD | standard | explicit | The Full Meeting with Jessica Afterward — What She Wasn't Putting in Dispatches | set_flag → ca_prot_01_agreed | CA_PROT_01_A_BTN2
CA_PROT_02_AGREE | LE LOUP-GAROU OF RIVIÈRE-DU-LOUP: FORMALLY ACKNOWLEDGED BY THE REPUBLIC | standard | explicit | The Night the Wolf Stopped Running — What Clear-Water Told You Privately | set_flag → ca_prot_02_agreed | CA_PROT_02_A_BTN2
CA_PROT_03_AGREE | LES FEUX FOLLETS FORMALLY ACKNOWLEDGED: THE SAINT JOHN MARSH ACCORD | standard | sensual | The Night Jessica Walked You Through the Marsh Herself to Show You What the Lights Mean | set_flag → ca_prot_03_agreed | CA_PROT_03_A_BTN2
CA_PROT_04_AGREE | MISHEPESHU PACT FORMALIZED: THE GREAT LYNX HOLDS THE ONTARIO WATERWAYS | standard | explicit | What Jessica Said Afterward About Why This One Required the Republic to Apologize First | set_flag → ca_prot_04_agreed | CA_PROT_04_A_BTN2
CA_PROT_05_AGREE | LA CORRIVEAU FORMALLY ALLIES WITH THE REPUBLIC — THREE GARRISONS EVACUATED THIS WEEK | standard | explicit | What Jessica Told You About What Corriveau Actually Wanted to Say — The Thing Not in the Dispatches | set_flag → ca_prot_05_agreed | CA_PROT_05_A_BTN2
CA_PROT_06_AGREE | LE CARCAJOU FORMALLY RECOGNIZED: THE MONCTON CORRIDOR ACCORD | standard | explicit | The Private Briefing — What Clear-Water Told You About Why the Carcajou Actually Accepted the Accord | set_flag → ca_prot_06_agreed | CA_PROT_06_A_BTN2
CA_PROT_07_AGREE | LA CHASSE-GALERIE: THE RIVER RUNS FOR THE REPUBLIC NOW | standard | sensual | The Night Mark Penoit Took You on the River and Told You the Full Story of How He Secured the Canoe for the Republic | set_flag → ca_prot_07_agreed | CA_PROT_07_A_BTN2
CA_PROT_08_AGREE | THE GOUGOU FORMALLY GUARDS THE CHALEUR BAY FOR THE CONTINENTAL ALLIANCE | standard | explicit | What Jessica Told You About the Gougou's Real Name — and What It Cost Her to Learn It | set_flag → ca_prot_08_agreed | CA_PROT_08_A_BTN2
PEACE_ALLIED_01 | PEACE OF [TILE_NAME] — THE CROWN EXPELLED FROM THE CONTINENT | standard | sensual | The Night After the Peace Was Signed — Ualani Carlisle and Jessica Clear-Water Celebrate Alone | set_flag → peace_allied_signed | PEACE_ALLIED_BTN2
PEACE_USA_01 | PEACE OF [TILE_NAME] — THE REPUBLIC HAS EXPELLED THE CROWN | standard | sensual | Ualani Carlisle Marks the End of the War in Her Own Way — Alone in the President's Office at Dawn | set_flag → peace_usa_signed | PEACE_USA_BTN2
WH_SECRET_01 | THE WHITE HOUSE AT MIDNIGHT — THE PRESIDENT WATCHES THE NEW YEAR ALONE | sensual | sensual | The Long Night of the New Year — What She Does with the Bottle and the Quiet | morale_boost | WH_SECRET_01_BTN2
WH_SECRET_07 | JULY AT THE WHITE HOUSE — INDEPENDENCE DAY IS ALSO HERS | explicit | explicit | The Night She Decided the Republic Was Worth Fighting For — and How She Spent It | morale_boost | WH_SECRET_07_BTN2
WH_SECRET_10 | INDIGENOUS PEOPLES DAY — A PERSONAL LETTER FROM JESSICA CLEAR-WATER ARRIVES | sensual | sensual | What Ualani Writes Back — and What She Does Not Put in the Letter but Means | nothing | WH_SECRET_10_BTN2
WH_SECRET_12 | CHRISTMAS IN WASHINGTON — THE PRESIDENT IS FAR FROM HOME | sensual | sensual | The Night the President Spent Christmas Alone in the White House — and Was Not Quite Alone | morale_boost | WH_SECRET_12_BTN2

## Govs & Cmds
STATUS | CATEGORY | SYSTEM / FEATURE | KEY FILE(S) | DESCRIPTION | GAPS / NOTES
Governor Core
FULL PASS | Governor Core | Governor Class | governor.gd | governorType (name string), governorLevel 1–3, governorArchetypeId (ARC_01–25 / CA_ARC_01+), loyalty −20 to +20, morale 0–100, isVicePresident bool, isLeader bool, questComplete bool. govMilModsLvl1/2/3 arrays hold tier-tiered mil mods. | morale var (0–100) may not be correctly initialized — see Major Bugs.
FULL PASS | Governor Core | Governor Loyalty | governor.gd, world.gd | loyalty −20 to +20 per turn via update_loyalty(). questComplete uncaps ceiling to +20. TURNCOAT event fires at loyalty ≤ −8. governor_loyalty_change outcome clamped ±20.
FULL PASS | Governor Core | tileMoralDecay | tile.gd, world.gd | 0–100 political corruption per tile. CORRUPT events fire at ≥50. tile_moral_decay_change outcome wired. Cleaner commander mod designed to reduce decay/turn (unimplemented).
FULL PASS | Governor Core | addMilMod() Pipeline | governor.gd addMilMod(type, levelCode) | Creates MilMod.new(), calls buildSelf(type) with Sprite2D guard, adds to govMilModsLvl1/2/3 based on levelCode (123/23/3). Programmatic mods work without scene node due to guard.
Named Governors
FULL PASS | Named Governors | Ualani Carlisle (President) | governor.gd | isLeader=true. Mods: Visionary×123, Champion of the Sun×23, Healer×3, President×123. Protagonist; drives win/lose. Full detail in Ualani tab. | Visionary/Champion/Healer mods have no calculateMilMods cases.
FULL PASS | Named Governors | Benjamin Tallmadge | governor.gd | Translator×123 (civilianMod). Espionage specialist.
FULL PASS | Named Governors | Patrick Henry / Abigail Adams / Thomas Paine / Joseph Warren | governor.gd | Historical named governors with unique mod assignments. Patrick Henry (Virginia orator), Abigail Adams (Massachusetts), Thomas Paine (radical pamphleteer), Joseph Warren (MA doctor/soldier).
FULL PASS | Named Governors | Daniel Shays / Phillis Wheatley / Francis Asbury | governor.gd | Daniel Shays (Shays' Rebellion leader), Phillis Wheatley (historical poet), Francis Asbury (Methodist bishop). All have unique mod sets per buildSelf().
Proc Gen
FULL PASS | Proc Gen | 25 USA Archetypes + 10 Canadian Archetypes | world.gd generateBarracksCommanders(), _apply_archetype_mods() | ARC_01–25: Wetlands Fisher, Appalachian Miner, Ivy League Dropout, Seminole Fighter, Green Mountain Farmer, Chesapeake Shipwright, Loyalist Turncoat, Tobacco Belt Drifter, War Widow, Indigenous Scout, Boston Rabble-Rouser, Continental Surgeon, Nantucket Sailor, Frontier Preacher, DC Bureaucrat, Rust Belt Steelworker, Plantation Deserter, Swamp Witch, Caribbean Privateer, Hawaiian Refugee, Border Mercenary, Acadian Forest Ranger, Gettysburg Descendant, LGBTQ+ Organizer, Carnival Barker. CA_ARC_01–10: French-Canadian equivalents with NP_06 name pool. Each archetype gets 4 mods: T1a×123, T1b×123, T2×23, T3×3.
FULL PASS | Proc Gen | Name Pool System (NP_01–06) | world.gd generateBarracksCommanders() | NP_01–05: USA cultural name pools by terrain/region affinity. NP_06: French-Canadian name pool. Pool selected by barracks tile terrain + cultural context.
Commander Arcs
FULL PASS | Commander Arcs | Arc Registration | WarRoomPanel.gd registerCommanderArc() | Called when governor hired. Builds arcData dict: governor, archetype_id, home_tile, objectives[3], objectives_complete[3], arc_active, arc_complete flags.
FULL PASS | Commander Arcs | 19 Objective Condition Evaluators | WarRoomPanel.gd checkObjectives(), evaluateCondition() | liberate_tile_terrain, liberate_specific_tile, liberate_tile_count, hold_tile_turns, commander_present_in_tile, liberate_tile_with_feature, turns_survived, build_in_home_tile, home_tile_corruption_below, home_tile_moral_decay_below, resource_threshold, liberate_tiles_in_state, home_tile_has_building, liberate_any_with_building, liberate_state_count + 4 more. Called each turn from world.gd _on_next_turn_pressed().
FULL PASS | Commander Arcs | Arc Event Firing | WarRoomPanel.gd → EventDatabase | arcObjectiveCompleted signal fires ARC_xx_FIRST (obj 1 done) and ARC_xx_DONE (all done). 50 total events across all 25 archetypes.
Commander Progression
FULL PASS | Commander Progression | Turn-Count Progression (CMD Events) | world.gd _commander_turns dict | turns_served tracked per governor. CMD_MERIT at 5t (level→1), CMD_RECOGNITION at 20t (→2), CMD_THANKS at 50t (→3). promote_commander outcome bumps governorLevel → activates higher-tier mods. CMD_THANKS has explicit button.
FULL PASS | Commander Progression | Governor Level + Mod Tier Activation | army.gd commanderCheck() | governorLevel 1: T1 mods only; level 2: T1+T2; level 3: T1+T2+T3. commanderCheck() selects appropriate govMilModsLvl and distributes to units.
VP System
FULL PASS | VP System | Vice President (isVicePresident) | army.gd addUnitCommander(), governor.gd | isVicePresident=true: all mods doubled (govMilModsLvl arrays appended twice). Gains Election Season mod. Loyalty doubled during election season. Can be any named or procedural governor. | VP status set via event outcome; no dedicated appointment UI.

## Game Systems
STATUS | CATEGORY | SYSTEM / FEATURE | KEY FILE(S) | DESCRIPTION | GAPS / NOTES
Core World
FULL PASS | Core World | Turn / Date System | world.gd, tile.gd | currentWorldTurn + month (1–12). evaluateDateEvents() called each turn. Month wraps → seasonal changes, storm spawns, calendar events. _on_next_turn_pressed() is the main turn-end loop.
FULL PASS | Core World | Tile Ownership | world.gd, tile.gd | tileOwner string per tile. OwnedTileList on country. liberate_tile / lose_tile outcomes update ownership and fire CL/CX events. Presidential claim calculated from owned tiles.
FULL PASS | Core World | Resource System | world.gd, country.gd | 12 resources: food, gold, weapons, manpower, wood, metal, magic, science, culture, influence, harmony, faith. _apply_resource_change(resource, amount) on country. Army costs deducted each turn via surveySelf() aggregation. | Weapon cost calc uses legacy names — new weapon armies report 0 cost.
FULL PASS | Core World | Building System | tile.gd, building.gd | tileBuildingsList per tile. disabled_buildings dict. disable_building / enable_building outcomes. Barracks, Forge, Courthouse, Fortress etc. checked in event conditions.
FULL PASS | Core World | Presidential Claim System | world.gd _calculate_presidential_claim() | Calculates republic legitimacy score from owned tiles + loyalty + morale. Drives secession + legitimacy crisis events.
FULL PASS | Core World | State Secession | world.gd checkStateSecessionConditions() | rebel_ flag per state. STATE_REBEL_01 → STATE_REINTEGRATED_01 chain. Mass secession cascades toward _execute_republic_collapse(). | Individual cascade logic to full collapse is partial.
FULL PASS | Core World | Republic Collapse | world.gd _execute_republic_collapse() | UK receives coastal tiles (182, 65-67, 151, 114, 123, 195). Interior tiles grouped by state code → spawn state country objects. USA retains DC (tile 188). COLLAPSE_02 fires. _republic_collapsed flag set. | No game-over sequence wired post-collapse.
FULL PASS | Core World | Weather / Storm System | tile.gd, world.gd _tick_storms(), _spawn_storm() | Storms spawn 3%/turn on random tile. Type by winterScore+terrain. Spreads to TileNeighbors; duration 2–6 turns; intensity 1–3. Types: Tornado, Hurricane, Thunderstorm, Blizzard, Nor'easter, Fog. _apply_storm_debuffs() applies status effects to armies in storm tiles each turn start.
FULL PASS | Core World | Winter Score + Supply Drain | tile.gd winterScore, world.gd _apply_winter_army_drain() | winterScore per tile (−80 to 80+). Categories: Extreme Hurricane → Blizzard. Months 11–2: food drain per army by cold category. Cold Weather armyTag exempts.
Factions
FULL PASS | Factions | Faction System | faction_control.gd, world.gd | Loyalty scores per faction; changeFactionLoyalty(). 9 USA factions defined. faction_loyalty_change outcome wired in executeOutcome().
PARTIAL | Factions | Espionage System | tile.gd, world.gd | espionageActive flag on tile. has_neighbor_with_espionage() helper. Culper Ring flag. sabotaged/reconDebuffed army flags set by spy outcomes. Wired to UALANI_CULPER_01 event condition. | No spy unit type. No full spy action loop. Army flag wiring from events is partial.
PARTIAL | Factions | Codebook / Spell Schools | world.gd, spell_schools_control.gd | levelUpSchool(); spell school tiers defined; protector spell unlocks referenced. TotalMagic on country drained by protector buff upkeep. | Full casting loop (player selecting and casting spells) TBD.
UI
FULL PASS | UI | Camera / Map Navigation | camera_movement_controller.gd | Pan/zoom; tile click-to-select; path control. Army drag/movement.
FULL PASS | UI | Resource Bar | ResourceBar.gd | Displays all 12 resource totals. Updates on turn end.
FULL PASS | UI | Military Panel | military_panel_control.gd | Army roster; unit list; commander picker; Melee/Ranged attack buttons. attackBlocked + reinforcementBlocked flags checked before triggering battles. | Visual category separator labels TODO (minor cosmetic).
FULL PASS | UI | Governor Selection Panel | governor_selection.gd | Shows governor level + loyalty; assign to tile; pick from available pool.
FULL PASS | UI | War Room Panel | WarRoomPanel.gd | Commander arc tracking; 3-objective display per active governor. registerCommanderArc() + checkObjectives() evaluated each turn. | Checkmark/circle art assets not yet loaded (TODO in WarRoomPanel.gd:33).
PARTIAL | UI | Tech Tree | tech_tree.gd | UI exists; add_tech outcome wired in executeOutcome(). Research nodes defined. | Full research action loop (player spending resources to research) TBD.
PARTIAL | UI | Civilian Control | civilian_control.gd, civilian_action_buttons.gd | Civilian unit action buttons; some wired. Park Ranger, Cartographer etc. defined. | Most civilian tool mod gameplay effects are IDEA-tier — no per-turn hooks.
PARTIAL | UI | Path / Movement Control | path_control.gd, army.gd | pathLine and targetTile vars; movement across tiles via tile cost system. Road level reduces cost. Cold Weather exemptions. | 'Not enough movement points' indicator TODO (path_control.gd:204).
Spawn
FULL PASS | Spawn | Barracks Army Generation (game start) | world.gd generateBarracksCommanders() | On game start: scans all player barracks tiles, selects archetype by terrain, generates commander, calls _apply_archetype_mods(), assigns to tile army. Canadian barracks use CA_ARC pool.
FULL PASS | Spawn | Army Template from CSV | army_database.gd, data/armies/army_templates.csv | army_templates.csv: ArmyName, country, tile, armyMods (pipe-delimited tags). armyTags populated from armyMods column at spawn.

## Win & Lose
STATUS | CATEGORY | SYSTEM / FEATURE | KEY FILE(S) | DESCRIPTION | GAPS / NOTES
Lose: Collapse
FIRST PASS | Lose: Collapse | _execute_republic_collapse() — Full Fragmentation | world.gd ~line 1925 | Triggered when republic morale/legitimacy reaches critical threshold. UK receives coastal tiles (182, 65-67, 151, 114, 123, 195). Interior tiles grouped by state code → spawn independent state country objects. USA retains only DC (tile 188) — Ualani's last stronghold. _republic_collapsed flag set. COLLAPSE_02 fires. | Game continues after collapse — no automatic lose sequence. Player can theoretically rebuild from DC. Rebuild win path is IDEA.
FIRST PASS | Lose: Collapse | COLLAPSE_01 — 'The Republic Has Fallen' | events.csv | Fires when all major metropolitan tiles are lost / surrender terms triggered. All major city falls consolidated into this narrative event. Explicit content buttons available. | No game-over screen wired to this event.
FIRST PASS | Lose: Collapse | COLLAPSE_02 — 'Washington Stands Alone' | events.csv, world.gd _execute_republic_collapse() | Fired directly from _execute_republic_collapse(). Ualani's final stand narrative. DC as last holdout. Explicit content option. Represents deepest lose state currently modeled. | No game-over trigger wired after this event.
Lose: Death
FIRST DRAFT | Lose: Death | Head of State Death → Game Over | world.gd ~line 4001 | _game_ended bool flag exists and is checked in election logic. Code priority comment: 'head of state death → game over (Ualani for USA)'. TODO: '# call _trigger_game_over() once game over screen exists'. | Game over screen scene not built. Ualani death has no mechanical consequence yet. HIGH PRIORITY for ship.
Lose: Secession
FIRST PASS | Lose: Secession | State Secession Cascade | world.gd checkStateSecessionConditions() | rebel_ flags per state fire STATE_REBEL_01 and remove tiles from player control. Reintegration via STATE_REINTEGRATED_01 possible. Mass secession feeds into _execute_republic_collapse() path. | Individual cascade logic from multi-state secession to full collapse is partial.
Lose: Occupation
IDEA | Lose: Occupation | Full Territory Loss | (no implementation) | Design intent: losing all player-controlled tiles → game over. No zero-tiles check exists. No loss-on-zero-territories logic.
Win: Unification
IDEA | Win: Unification | Full Continental Unification | (no implementation) | Design intent: liberate all US + Canadian territories → victory. No all-tiles-owned check. No victory screen. | Most important win condition to define and implement.
Win: Diplomatic
IDEA | Win: Diplomatic | Canadian Alliance + UK Peace Treaty | events.csv (CAN_PEACE_01, PEACE_ALLIED, PEACE_USA) | Peace treaty events are authored (CAN_PEACE_01, PEACE_ALLIED, PEACE_USA). Design intent: achieving diplomatic resolution = win state or major milestone. No win-condition check fires from these event outcomes.
Win: Protectors
IDEA | Win: Protectors | All 25 Protectors Agree | events.csv PROT_xx_AGREE + CA_PROT_xx_AGREE | All 17 USA + 8 Canadian protectors have AGREE stage events fully authored. Design intent: recruiting all 25 = win trigger or major milestone. No all-protectors-agreed win check exists.
Win: Screen
IDEA | Win: Screen | Victory + Game Over Screens | (no implementation) | No victory screen UI. No game over screen UI. _game_ended flag exists but has no visual/audio/mechanical consequence. Both screens required for any playable build. | HIGHEST PRIORITY for any public demo or ship candidate.

## Major Bugs
SEVERITY | BUG | FILE / LINE | DESCRIPTION | SUGGESTED FIX
CRITICAL | _apply_army_buff() is a complete stub | world.gd _apply_army_buff() ~line 3351 | Function is called by event button outcomes with army_buff outcome type but the entire body is a single `pass` statement — does nothing. Every army_buff event outcome in the entire game is silently ignored. | Implement: iterate countryArmyList, filter by tile if provided, call army.apply_status(buff_type, duration) for matching armies.
HIGH | Game over / victory screens not implemented | world.gd ~line 4001; (no scene file) | _game_ended bool and _game_won bool exist. Head of state death check written with TODO comment. No GameOver scene. No Victory scene. _trigger_game_over() is referenced but not defined. | Build GameOver and Victory scenes. Define _trigger_game_over() and _trigger_game_victory(). Wire to head-of-state death and win condition checks.
HIGH | Explicit content has no global settings toggle | event_scene.gd _build_buttons(); settings system | button_type filtering code exists in event_scene.gd but no global Settings.enableExplicit flag was found. Explicit buttons render unconditionally for all players regardless of preference or age. | Add Settings.enableExplicit bool (default false). Check it in _build_buttons() before rendering explicit/kinky_lewd buttons. Add toggle to settings menu.
MEDIUM | morale vs loyalty: commander bonus may always be 1.0× | army.gd surveySelf() ~line 371 | Morale multiplier uses commander.morale (0–100 field) but governor.gd tracks loyalty (−20 to +10). If morale is never set/initialized it stays 0, so armyPunch multiplier is always ×1.0 — no commander ever gives a bonus. | Audit governor morale initialization. Map loyalty to 0–100 for morale input, or verify a separate morale var is correctly set.
MEDIUM | Weapon cost calc uses legacy weapon names only | army.gd surveySelf() lines ~357-365 | Match block calculating armyWeaponsCost checks old DODK names (Spear, Club, Atlatl). No case for Cutlass, Flintlock, Field Gun, etc. All new-weapon armies show 0 weapons cost. | Add Saber/Musket/Artillery weapon cost cases to the match block.
MEDIUM | commanderCheck() accumulates duplicate mods on repeated updateArmyUI calls | army.gd commanderCheck() | commanderCheck() appends mods to each unit on every call. Units clear militaryModifierList in getUnitAttributes() but commanderCheck runs after. Rapid successive updateArmyUI calls can double/triple mods on units. | Verify getUnitAttributes() fully clears militaryModifierList before commanderCheck. Audit call order in updateArmyUI().
MEDIUM | No UI for active army status effects | army.gd armyStatusEffects; military panel | Army can have Diseased, Routed, Terrified, Waterlogged etc. active with no visual feedback. Player cannot see what statuses are active or how many turns remain. | Add status effect icon row to military panel or army tooltip. Iterate armyStatusEffects and display type + turnsLeft.
LOW | armyShield vs armyMaxShield display inconsistency | army.gd updateFinalTotals() | updateFinalTotals() passes armyShield for both current and max in armyCostUI3. Shield depletion bar never shows correctly. | Change: armyCostUI3.updateSelf(armyShield, armyMaxShield).
LOW | Nassau/BA faction logic stub | country.gd ~line 1180 | Comment: 'TODO: BA (Nassau) is opportunist — logic stub'. Bahamas has no behavioral AI logic implemented. | Implement opportunist faction behavior for BA country.
LOW | ~25 debug print statements throughout codebase | Various .gd files | print() debug statements: 'DEBUG CLICK', 'RETURN DEBUG', 'ARMYARRIVEDDEBUG', 'ControlDEBUG' etc. Non-critical but noisy in console. | Search for print( and remove/comment all debug prints before any public build.
LOW | No 'not enough movement points' UI feedback | path_control.gd ~line 204 | TODO comment in path_control.gd. Player gets no visual indication when they try to move an army without sufficient movement points. | Add tooltip or panel flash when movement fails due to insufficient points.
LOW | War Room arc checkmark/circle art assets missing | WarRoomPanel.gd:33-34, CommanderArcEntry.gd:33-34 | TODO comments: load checkmark and circle assets for objective display icons. Currently no visual state indicator for completed vs incomplete objectives. | Load and wire checkmark/circle textures for arc objective UI nodes.